## Summary
Phase-Exit Review
Organisation / Department: | UPF Gestió de projectes
Project Name: | Aigua Clara
Project Owner: | Aigües de Barcelona
Project Core Team Number: | T202.A
Project Core Team members: | Maria Beili Mena Dorado, Alex Fernández de Alarcon, Sergi Rodríguez, Pol Serrat, Ferran Sordé i Martí Vilaró
Reviewer Name: | Rebeca Calderón or Elisabet Duocastella
Overall Compliance (%) | 48.49%
Overall Phase-Exit Status: | 0.48488
Area | Phase-Exit Status | % of Phase Compliance | Date | Already performed?
Project Initiation | 86.84% | 86.84% | 2025-09-27 | Yes
Iteration | 58.62% | 58.62% | dd/mm/yyyy | Yes
Project Closure | 0% | 0% | dd/mm/yyyy | No
Assessment Key:
0.3 | Major key activities for the phase(s) weren't performed (50% of the key activities or more are still to be completed).
0.7 | Some key activities are still to be completed before the phase(s) can be closed (% of compliance between 51% and 80%).
0.9 | Nearly all the key activities for the phase(s) are complete (more than 80% of the key activities). The decision to move to another phase should be taken considering the relevance / adequacy of the remaining activities to the project and its specificities.
Yes
No

## Project Initiation
| Project Initiation Phase-Exit Checks |  | Date: | 2025-09-27
% of Phase Compliance |  |  | 86.84% | 86.84%
# | Description | Answer | Score | Comments
1 | Has a Project Initiation Request been documented and approved? | Yes, Partially | 5 | Està documentat, però no aprovat per SP i PSC
2 | Are the project context, scope, deliverables and expected outcomes documented? | Yes, Partially | 5 | No s'han definit els outcomes
3 | Has a Project Owner (PO) been identified? | Yes | 10 | Aigues de Barcelona es/serà el propietari
4 | Has the project theme been agreed with the challenge mentor? | No | 0 | No hem tingut reunió amb el/la mentor/a
5 | Are success criteria documented? | Yes | 10 | Fet | Yes
6 | Are the success criteria SMART? | Yes | 10 | Afegit | Yes, Partially
7 | Have all the key project stakeholders been identified? | Yes | 10 |  | No
8 | Are all the initial roles and responsibilities defined? | Yes | 10 |  | N/A
9 | Are major assumptions and constraints identified? | Yes | 10 | (Detallat al project charter)
10 | Have the major risks been identified? | Yes | 10 | (Detallat al project charter)
11 | Is there a Representative (REP) assigned to the project? | Yes | 10 | Representant: Maria Beili
12 | Has the PCT decided whether to include a Project Manager (PM) rol? | Yes | 10 | Project Manager: Martí Villaró
13 | Has a Project Charter been documented by the Project Core Team (PCT)? | Yes | 10 | Fet
14 | Is the project scope broken-down in manageable components that allow rough estimation of resources, work effort and duration? | Yes | 10
15 | Is the project work breakdown structure completed ? | Yes | 10
16 | Is the Project Initiation kick-off meeting planned? | Yes | 10
17 | Have all artifacts been placed in the project repository Google Drive? | Yes | 10
18 | Have all artifcats followed the configuration plan? | Yes | 10
19 | Is the project ready to proceed to the Iteration Phase? | Yes, Partially | 5 | Necessita ser aprovat per SP i PSC
| Total score for compliance | 0 | 165

## Iteration
| Iteration Phase-Exit Checks |  | Date: | dd/mm/yyyy
% of Phase Compliance |  |  | 58.62% | 58.62%
# | Description | Answer | Score | Comments
QUESTIONS TO BE ANSWERED AT THE END OF FIRST ITERATION
1 | Is the Stakeholder Matrix complete with all the relevant stakeholders' names and contact details? | Yes | 10
2 | Are all project roles and responsibilities detailed? | Yes | 10
3 | Is the project work breakdown structure completed ? | Yes | 10 |  |  | Yes
4 | Has the product scope been agreed with the challenge expert or mentor? | N/A | - | No, no tenim assignat un mentor |  | Yes, Partially
5 | Was the Project Work Plan baselined and approved by the Project Steering Committee (PSC)? | N/A | - | Encara no
6 | Is the Project Work Plan baselined and approved by the Project Steering Committee (PSC)? | N/A | - | Encara no |  | N/A
7 | Are all the communication items (e.g. meetings and reports) defined as well as their frequency? | N/A | -
8 | Is a Risk Management Plan documented as a separate document? | Yes | 10
9 | Has a configuration management procedure been documented? | Yes | 10
10 | Is there a Project Handbook documented? | Yes | 10 | Donat pels professors
11 | Are all the major deviations from the Project Charter approved by the Project Steering Committee (PSC)? | N/A | - | Encara no
QUESTIONS TO BE ANSWERED AT THE END OF FIRST ITERATION
12 | Have deliverables been performed as defined and scheduled in the work breakdown structure? | Yes | 10 | Totes les entregues s'han realitzat com tocava i en el termini indicat. | Yes
13 | Were artefacts produced, updated and revised as planned? | Yes | 10 | Correcte. | Yes, Partially
14 | Was the work breakdown structure refined at each iteration? | No | 0 | No l'hem modificat.
15 | Was the iteration work defined at the beggining of each iteration? | Yes | 10 | <Add a justification here.>
16 | Were the quality control activities performed as planned? | No | 0 | No s'ha fet plantejat un quality control | No
17 | Are all major risks mitigated? | No | 0 | No hem pogut implementar cap validació de les dades, ja que encara no les hem rebut. | N/A
18 | Have the products deliverables been agreed with the challenge expert or mentor? | No | 0 | Encara no tenim mentor.
19 | Have all the approved changes been implemented? | No | 0 | Encara no hem tingut feedback dels PSC ni mentors
20 | Are deliverables in line with requestor needs and expectations? | Yes | 10 | Sí, progressa adequadament.
21 | Are all the project issues and corrective actions resolved / closed? | Yes | 10 | Tot en ordre.
22 | Are all product deliverables ready to be approved by the Project Owner (PO)? | Yes | 10 | Feina feta.
23 | Are all project artifacts ready to be approved by the Solution Provider (SP)? | Yes | 10 | Les entregues s'han dut a terme.
24 | Were the relevant stakeholders informed about the delivery of projects outputs? | Yes, Partially | 5 | Tots aquells stakeholders coneguts han estat informats. Com hem mencionat anteriorment, encara no tenim mentor.
25 | Were project performance indicators and metrics captured and assessed? | No | 0 | No tenim dades
26 | Have all the communication items (meetings, reports,…) been implemented as planned? | Yes | 10
27 | Have all deliverables/artifacts been placed in the project repository Google Drive? | Yes | 10
28 | Have all deliverables/artifacts followed the configuration plan? | Yes | 10 | Segueixen el format requerit.
29 | Is the project ready to proceed to the Closing Phase? | Yes, Partially | 5 | A l'espera feedback i millores per part de PSC
| Total score for compliance | 0 | 170

## Project Closure
| Project Closure Phase-Exit Checks |  | Date: | dd/mm/yyyy
% of Phase Compliance |  |  | 0% | 0%
# | Description | Answer | Score | Comments
1 | Did a Project-End Review Meeting take place? | No | 0 | <Add here the justification for the answer given.>
2 | Has the product backlog been completed? | No | 0
3 | Did the Appropriate Governance Board (AGB) formally approve deliverables (Challenge Final Report)? | No | 0
4 | Were final project performance indicators and metrics assessed and compared to project baselines? | No | 0 |  | Yes
5 | Are project benefits and unachieved goals assessed and remaining benefits forecasted? | No | 0 |  | Yes, Partially
6 | Was client / requestor satisfaction assessed? | No | 0 |  | No
7 | In case some risks or issues couldn't be closed, are they re-assessed and follow-up actions recommended? | No | 0 |  | N/A
8 | Did all the relevant stakeholders give feedback on the overall project experience? | No | 0
9 | Were lessons learned and post-project recommendations captured? | No | 0
10 | Is the Project-End Report documented and delivered to the relevant stakeholders? | No | 0
11 | Have all deliverables been placed in the project repository Google Drive? | No | 0
12 | Have all deliverables followed the configuration plan? | No | 0
13 | Was the project formally accepted by the Project Steering Commitee (PSC), project-end report? | No | 0
14 | Have project team members performance been assessed? | No | 0
15 | Is the project ready to be closed? | No | 0
| Total score for compliance | 0 | 0