## Risk
Risk Identification and Description |  |  |  | Risk Assessment |  |  | Preventive Risk Response |  |  |  |  | Contingency Activities
ID | Custodian | Category | Description | Likelihood (L) | Impact (I) | Risk Level (L*I) | Risk Response Strategy | Action Details | New Likelihood (L) | New Impact (I) | New Risk Level (L*I) | Contingency activity & custodian | Trigger
R1 | Maria Beili Mena Dorado | External | Being selected as one of the 15 participant teams of the AB Data Challenege is key. Failing to do so would mean not having at our disposal all the data needed to develop the project. | 1 | 3 | 3 | Accept | Due to the nature of the risk, take a passive acceptance stance. So no preventive action can be taken. | 1 | 3 | 3 | Continue the project with only partial data. This could reduce the final accuracy of the project. But the project can still be done without the full data. | Failing to be chosen as one of the 15 participant teams.
R2 | Martí Vilaró | Staffing | There is a lack of water system experts in the team to validate whether the detection of outliers make physical sense. This poor capacity to verify whether an outlier actually corresponds to a leak or failure may make cheking the precision of our model difficult. | 2 | 2 | 4 | Reduce | Create different outlier detection methods and compare the results. | 1 | 2 | 2 | Use the mentorship with AB to ask about the validity of our results. | The outliers given by the diferent models are diferent.
R3 | Pol Serrat | IT | The dataset provided by AB may contain missing, inconsistent, or delayed data, which could affect model performance and accuracy. | 2 | 3 | 6 | Reduce | Implement data validation scripts and automated anomaly filters before training. | 2 | 1 | 2 | Use synthetic data or historical AB datasets to simulate missing inputs. | AB provides incomplete data files.
R4 | Ferran Sordé | Legal | Data privacy or confidentiality rules might limit data sharing or restrict use of sensitive customer information. | 1 | 3 | 3 | Avoid | Ensure anonymization and compliance with law. Ask AB representatives about it. | 1 | 1 | 1 | Replace sensitive fields with aggregated or synthetic data if needed. | AB’s data policy change.
R5 | Sergi Rodríguez | IT | The computational requirements for model training and evaluation might exceed available hardware or time constraints. | 2 | 2 | 4 | Reduce | Use optimized model architectures or cloud processing. | 2 | 1 | 2 | Use lighter models or sampling-based training. | Training jobs fail or exceed processing deadlines.
O1 | Maria Beili Mena Dorado | External | If we win the competition we may be able to work closely with AB’s engineers and data scientists. This can accelerate understanding of real-world water systems, leading to better model performance. | 1 | 3 | 3 | Accept | Due to the nature of the oportunity, take a passive acceptance stance. So no preventive action can be taken. | 1 | 3 | 3 | Use AB’s feedback to refine models and validate results directly with their infrastructure data. | Wining the competition.
O2 | Alex Fernández de Alarcon | Business | The developed anomaly detection model can be adapted for other cities or utilities facing similar challenges, creating future project or commercial opportunities. | 1 | 2 | 2 | Enhance | Develop modular, well-documented code with configurable inputs for other datasets. | 2 | 2 | 4 | Create a demo or open-source version showcasing the algorithm’s generality. | Successful validation of model performance beyond AB’s dataset.
O3 | Pol Serrat | Business | The anomaly detection system may identify previously undetected leaks, misuse, or sensor faults, offering AB significant operational value. | 1 | 2 | 2 | Exploit | Design output reports that highlight potential infrastructure issues for AB review. | 2 | 2 | 4 | Integrate with AB’s monitoring tools for live anomaly feedback. | Model correctly identifies true system anomalies confirmed by AB.
O4 | Martí Vilaró | People and Organisation | Working with real-world data from AB allows the team to gain practical experience in large-scale data cleaning, time-series analysis, and anomaly detection. | 2 | 2 | 4 | Exploit | Document challenges and insights during data preprocessing for educational and future research use. | 3 | 2 | 6 | Summarize all methodology and findings in a final report. | Successful preprocessing and feature extraction from AB’s datasets.

## Issue
Cause | Effect | Impact | Response | Custodian | Dates
[5 empty] | Identification | Occurrence | Closure

## Change
Requester | Request description | Impact | Alternatives | Response | Custodian | Dates
[6 empty] | Request | Acceptance | Applied

## Lessons learned
Lessons learned | Category | Effect | Impact | Data
Identification