Project Title: Aigua Clara

Team Number: 202A

| ITERATION** 2nd | Overall Status: Amber Esperem poder resoldre i complir amb els objectius establerts després de la primera mentoria. Necesitem compendre les dades que tenim actualment per poder avançar. |
| --- | --- |
| SP: Rebeca Calderón PCT: Maria Beili Mena Dorado Alex Fernández de Alarcon Sergi Rodríguez Pol Serrat Ferran Sordé Martí Vilaró | Issues Status: Amber - List: - Publicació de les dades massa tardia: Les dades no es van publicar fins el 4 de novembre, cosa que ens ha endarrerit per començar a desenvolupar el nostre producte. - Dificultats en netejar i entendre les dades del dataset d’Aigües de Barcelona. Qualitat regular de les dades. |
| Project Status Summary A data del 9 de novembre, hem portat a terme allò que teníem planificat fins ara. A continuació, comencem la fase d’execució del projecte, on procedirem a realitzar un procés de neteja de dades abans de començar a construir el model en qüestió. |  |
|  | Project Changes Major changes: Green Actualment no s’ha planificat cap canvi en el projecte. Un cop realitzada la primera mentoria, és possible que es realitzin canvis per redirigir el projecte si es que així es requereix. |
|  | Top Risks Status: Amber - Active: <x> - Incertesa en la presa de decisions: Es possible que ens toqui refer una part important del projecte - Dades no valides o pobres. |
| WORK BREAKDOWN STRUCTURE A continuació afegim el WBS: en verd tasques ja fetes, ambar en proces, vermell pendents. |  |

Work Breakdown Component Description

1.1 Project Charter Document the project’s purpose, scope, objectives, and stakeholders to formally authorize the project’s initiation. Estimate: 3 hours Responsibles: Maria Beili Mena Dorado (REP) Due date: 12/10/2025

2.1 Project Work Plan Develop a detailed plan outlining project tasks, timelines, resources, and milestones for execution and monitoring. Estimate: 2 hours (per iteration) Responsible: Sergi Rodríguez (PCT) Due date: 12/10/2025 – 19/10/2025 – 02/11/2025 – 16/11/2025 – 30/11/2025

2.2 Project Stakeholder Matrix Identify all project stakeholders and map their influence, interest, and engagement strategies to ensure effective communication. Estimate: 2 hours (per iteration) Responsible: Martí Vilaró (PM) Due date: 19/10/2025 – 02/11/2025 – 16/11/2025 – 30/11/2025

3.1 Project End Report Summarize project outcomes, deliverables, lessons learned, and performance against objectives upon project completion. Estimate: 6 hours Responsible: Maria Beili Mena Dorado (REP) Due date: 07/12/2025

4.1.1 Change Log Maintain a record of all project changes, documenting approvals, reasons, and impacts on scope, schedule, or budget. Estimate: 1 hour (per iteration) Responsible: Alex Fernández de Alarcon (PCT) Due date: 19/10/2025 – 02/11/2025 – 16/11/2025 – 30/11/2025

4.1.2 Risk Log List and assess potential project risks, along with mitigation strategies and status updates throughout the project lifecycle. Estimate: 1 hour (per iteration) Responsible: Pol Serrat (PCT) Due date: 19/10/2025 – 02/11/2025 – 16/11/2025 – 30/11/2025

4.1.3 Issue Log Track project issues as they arise, recording resolutions, responsibilities, and timeframes for closure. Estimate: 1 hour (per iteration) Responsible: Ferran Sordé (PCT) Due date: 19/10/2025 – 02/11/2025 – 16/11/2025 – 30/11/2025

4.2 Project Phase-Exit Review Checklist Develop a checklist to evaluate project readiness and confirm completion of deliverables before moving to the next phase. Estimate: 30 min (per iteration) Responsible: Maria Beili Mena Dorado (REP) Due date: 12/10/2025 – 26/10/2025 – 09/11/2025 – 23/11/2025 – 07/12/2025

5.1.1 Individual Participant Registration Sign up individually to the AB challenge. Estimate: 10 min Responsible: Maria Beili Mena Dorado (REP) Due date: 12/10/2025

5.1.2 Group Project Registration Send our team registration to the AB challenge. Estimate: 1 hour Responsible: Maria Beili Mena Dorado (REP) Due date: 19/10/2025

6.1 AB Data Collection Sign the document and wait for AB to send the data. Estimate: 1 hour Responsible: Maria Beili Mena Dorado (REP) Due date: 02/11/2025

6.2.1 Assess External Data Need Determine whether additional external data sources are needed to supplement project analysis. Estimate: 1.5 hours Responsible: Martí Vilaró (PM) Due date: 02/11/2025

6.2.2 Collect External Data Acquire and validate external datasets in accordance with project data quality and compliance standards. Estimate: 4 hours Responsible: Alex Fernández de Alarcon (PCT) Due date: 02/11/2025

7.1 Implementation of Exploratory Data Analysis Conduct exploratory data analysis to identify trends, patterns, and anomalies in the collected data. Estimate: 3 hours Responsible: Sergi Rodríguez (PCT) Due date: 09/11/2025

7.2 Evaluation of Exploratory Data Analysis Review and interpret EDA results to refine data understanding and inform modeling decisions. Estimate: 1 hour Responsible: Pol Serrat (PCT) Due date: 09/11/2025

7.3 Refine Data Clean, transform, and format data to prepare it for advanced analysis and modeling based on the EDA. Estimate: 2 hours Responsible: Pol Serrat (PCT) Due date: 09/11/2025

8.1 Assess Models Usefulness Evaluate potential analytical models for their suitability, relevance, and alignment with project objectives. Estimate: 1.5 hours Responsible: Martí Vilaró (PM) Due date: 16/11/2025

8.2 Implement Models Develop and configure selected models, ensuring accurate integration with project data. Estimate: 6 hours Responsible: Sergi Rodríguez (PCT) Due date: 16/11/2025

8.3 Train Models Train models using prepared datasets to optimize accuracy and predictive performance. Estimate: 3 hours Responsible: Ferran Sordé (PCT) Due date: 16/11/2025

9.1 Implementation of Models Evaluation Test and evaluate model performance against validation data to assess accuracy and reliability. Estimate: 2 hours Responsible: Sergi Rodríguez (PCT) Due date: 16/11/2025

9.2 Improve Models Refine and adjust model parameters to enhance performance and correct identified deficiencies based on the models evaluation. Estimate: 5 hours Responsible: Ferran Sordé (PCT) Due date: 16/11/2025

10.1 Design of the Graphical Interface Structure Create the layout and structure for the project’s graphical user interface, focusing on usability and design logic. Estimate: 2 hours Responsible: Alex Fernández de Alarcon (PCT) Due date: 23/11/2025

10.2 Implementation of the Graphical Interface Code Develop and test the functional code for the graphical interface based on approved design specifications. Estimate: 2 hours Responsible: Sergi Rodríguez (PCT) Due date: 23/11/2025