UPF – Gestió de projectes

GP2526 Project Work Plan

Aigua Clara

Document Control Information

| Settings | Value |
| --- | --- |
| Document Title: | Project Work Plan |
| Project Title: | Aigua Clara |
| Team Number: | 202.A |
| Project Owner: | Aigües de Barcelona (AB), Sheila Piñol |
| Project Core Team: | Maria Beili Mena Dorado, Alex Fernández de Alarcon, Sergi Rodríguez, Pol Serrat, Ferran Sordé i Martí Vilaró |

| Revision | Date | Created by | Short Description of Changes |
| --- | --- | --- | --- |
| v0.1 | 7/oct/25 | Pol Serrat | Initiation: 2.2 Section and PM Branch |
| v1.0 | 15/oct/25 | Alex Fernández de Alarcon | Iteration 1: First Full Version of the PWP. |
| v3.1 | 31/oct/25 | PST | Applied professor's feedback (v1.0) and filename alignment (v3.1) |

The latest version of this controlled document is stored in Google Drive\GP2025-26\Subject global documents\Project methodology and templates\

- Introduction

  - Project summary

Advanced data analysis techniques offer new opportunities to understand and characterize water consumption patterns. In this project we will develop a model capable of detecting anomalous consumption based on real data from Aigües de Barcelona remote reading. The implementation of this solution will significantly improve the detection of situations that exceed normality, facilitating a more efficient management of the service and promoting a more responsible use of hydraulic resources. This approach will allow us to identify irregularities such as leaks, technical malfunctions, or unexpected behavioral changes in consumption at an early stage. By integrating artificial intelligence and/or statistical learning methods, the model will continuously adapt to new data, increasing its precision over time. The results obtained can be used to educate among users and institutions about sustainable water management. This project aims to combine technology, environmental responsibility, and innovation to contribute to a smarter and more efficient urban water system.

  - Success Criteria and Critical Success Factors

Success Criteria

The objective is to create a technological solution that allows for the automatic detection of anomalies in user consumption to prevent and find unusual patterns such as leaks. Success is measured based on whether the result obtained for our service coincides with a real case of anomalous consumption and whether this can be detected in advance. The SMART objectives are the following:

- Project objectives: meet all the milestones of the work plan within the established deadlines.

- Product objectives: achieve a minimum accuracy of 75% in the detection of anomalies in the analyzed data.

- Business objectives: demonstrate the technical feasibility and social value of the project to Aigües de Barcelona, ​​highlighting its positive impact on sustainability and efficiency.

Basically, transform the environment and consumption of people in the metropolitan area of ​​Barcelona by improving management and promoting responsible consumption.

Critical Success Factors

In order to successfully complete the project, we need the involvement of all stakeholders, good data quality, dedication from team members in the development of the project and having clear Statements and outs from the team and the mentor. It will also be necessary for team members to have the necessary technical knowledge to develop the alert system.

  - Project Stakeholders

The main stakeholders involved in the project are the Project Owner (PO): Jordi Mora representing Aigües de Barcelona, Business Manager (BM): mentor from  Aigües Barcelona, Solution Providers (SP): Project evaluators (teachers), Team Representative (TR): Maria Beili, Project Manager (PM): Martí Villaró, Project Core Team (PCT): 202.A team members, Project Steering Committee (PSC): PO, SP, BM, PM and Business Implementation Group (BIG): Aigües Barcelona users and investors. Full detail of the project stakeholders can be found in the document Team202A.ProjectStakeholderMatrix.vx.y

  - Project Constraints / Assumptions

We have identified some initial assumptions and constraints, which could be expanded as we move forward doing the project.

Assumptions:

1. The given data are correct, complete and representative. They have been carefully checked to ensure reliability and consistency, so all analyses and decisions can be based on facts. If any updates or corrections are needed in the future, they will be reviewed and shared with the team.

2. AB will maintain an active communication and participation with the teams. This includes participating in several meetings, providing feedback, and supporting coordination between different areas. AB will also make sure that everyone stays informed about progress, upcoming tasks, and any important project developments.

3. All team members will be equally involved in each phase of the project.

Constraints:

1. Time limit: We must stick to the schedule set by AB and follow their time line.

2. Personal limitations: We are only six people to carry out the entire project, we should   think twice before setting any objective, see if we are capable of achieving it. We should make sure that each goal is realistic and achievable within our capacities, distributing tasks efficiently to maintain a balanced workload.

3. Resources limit: We have a limited amount of resources provided by the University and AB such as technological tools, advice or personal experience inside AB and  from which point of view we should aim our project, therefore, we need to use these resources wisely and focus our project in a direction that makes the best use of the available support and guidance.

4. We don’t have a financial budget for the development of the project.

- PRODUCT SCOPE

Develop a functional prototype capable of detecting patterns of anomalies in the water consumption of Aigües de Barcelona users using Machine Learning algorithms.

We will be responsible for:

- Processing and cleaning the data provided by Aigües de Barcelona.

- Developing and training a model capable of detecting and understanding irregular water consumption patterns.

- Presenting a model integration to show the found results.

- Managing the administrative actions required to participate in the Aigües de Barcelona competition.

- Submitting project initiation documents (Project Charter).

- Submitting project planning documents (Project Work Plan, Project Stakeholder Matrix).

- Submitting project execution documents (Project Status Report).

- Submitting project closure documents (Project End Report).

- Submitting project monitoring and control documents (Project Logs, updated Project Work Plan, Project Phase-Exit Review Checklist).

- Preparing the final presentation for the Aigües de Barcelona competition.   CANCELLED

We will not be responsible for:

- Taking action in case an anomaly is detected.

- Deploying the model on Aigües de Barcelona’s servers.

- Maintaining or updating the model over time.

  - Requirements

| ID | Name Short name of the requirement | Description | Category Requested by | Deliverable ID |
| --- | --- | --- | --- | --- |
| Rq1 | Data Collection and Cleaning | The system must be capable of processing and cleaning large datasets of water consumption | Functional Requirement - Aigües de Barcelona | 1.3.1.1 |
| Rq2 | Anomaly Detection Model | Develop and train a Machine Learning model able to identify anomalies in the consumption patterns. | Functional Requirement - Aigües de Barcelona | 1.3.1.3 |
| Rq3 | Dashboard for Visualization | Provide a simple dashboard or visualization tool that displays identified anomalies. | Feature / Functional Requirement - Aigües de Barcelona | 1.3.1.5 |
| Rq4 | Documentation | Deliver all project documentation for the usage of the project | Support Requirement - UPF(teachers) | 1.4.1 |

  - Work Breakdown Structure

| Work Breakdown |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1 |  | Initiation Documents |  |  |
| 1.1 |  |  | Project Charter |  |
| 2 |  | Planning Documents |  |  |
| 2.1 |  |  | Project Work Plan |  |
| 2.2 |  |  | Project Stakeholder Matrix |  |
| 3 |  | Closure Documents |  |  |
| 3.1 |  |  | Project End Report |  |
| 4 |  | Monitoring and Control Documents |  |  |
| 4.1 |  |  | Project Logs |  |
| 4.1.1 |  |  |  | Change Log |
| 4.1.2 |  |  |  | Risk Log |
| 4.1.3 |  |  |  | Issue Log |
| 4.2 |  |  | Project Phase-Exit Review Checklist |  |
| 5 |  | Participation in Aigües de Barcelona Contest |  |  |
| 5.1 |  |  | Contest Registration |  |
| 5.1.1 |  |  |  | Individual Participant Registration |
| 5.1.2 |  |  |  | Group Project Registration |
| 5.2 |  |  | Final Project Submission CANCELLED |  |
| 5.3 |  |  | Final Project Presentation CANCELLED |  |
| 6 |  | Data Collection |  |  |
| 6.1 |  |  | AB Data Collection |  |
| 6.2 |  |  | External Data Collection |  |
| 6.2.1 |  |  |  | Assess External Data Need |
| 6.2.2 |  |  |  | Collect External Data |
| 7 |  | Exploratory Data Analysis |  |  |
| 7.1 |  |  | Implementation of Exploratory Data Analysis |  |
| 7.2 |  |  | Evaluation of Exploratory Data Analysis |  |
| 7.3 |  |  | Refine Data |  |
| 8 |  | Models Selection and Training |  |  |
| 8.1 |  |  | Assess Models Usefulness |  |
| 8.2 |  |  | Implement Models |  |
| 8.3 |  |  | Train Models |  |
| 9 |  | Models Evaluation and Improvement |  |  |
| 9.1 |  |  | Implementation of Models Evaluation |  |
| 9.2 |  |  | Improve Models |  |
| 10 |  | Model Integration (Visualization) |  |  |
| 10.1 |  |  | Design of the Graphical Interface Structure |  |
| 10.2 |  |  | Implementation of the Graphical Interface Code |  |

Work Breakdown Component Description

1.1 Project Charter Document the project’s purpose, scope, objectives, and stakeholders to formally authorize the project’s initiation. Estimate: 3 hours Responsibles: Maria Beili Mena Dorado (REP) Due date: 12/10/2025

2.1 Project Work Plan Develop a detailed plan outlining project tasks, timelines, resources, and milestones for execution and monitoring. Estimate: 2 hours (per iteration) Responsible: Sergi Rodríguez (PCT) Due date: 12/10/2025 – 19/10/2025 – 02/11/2025 – 16/11/2025 – 30/11/2025

2.2 Project Stakeholder Matrix Identify all project stakeholders and map their influence, interest, and engagement strategies to ensure effective communication. Estimate: 2 hours (per iteration) Responsible: Martí Vilaró (PM) Due date: 19/10/2025 – 02/11/2025 – 16/11/2025 – 30/11/2025

3.1 Project End Report Summarize project outcomes, deliverables, lessons learned, and performance against objectives upon project completion. Estimate: 6 hours Responsible: Maria Beili Mena Dorado (REP) Due date: 07/12/2025

4.1.1 Change Log Maintain a record of all project changes, documenting approvals, reasons, and impacts on scope, schedule, or budget. Estimate: 1 hour (per iteration) Responsible: Alex Fernández de Alarcon (PCT) Due date: 19/10/2025 – 02/11/2025 – 16/11/2025 – 30/11/2025

4.1.2 Risk Log List and assess potential project risks, along with mitigation strategies and status updates throughout the project lifecycle. Estimate: 1 hour (per iteration) Responsible: Pol Serrat (PCT) Due date: 19/10/2025 – 02/11/2025 – 16/11/2025 – 30/11/2025

4.1.3 Issue Log Track project issues as they arise, recording resolutions, responsibilities, and timeframes for closure. Estimate: 1 hour (per iteration) Responsible: Ferran Sordé (PCT) Due date: 19/10/2025 – 02/11/2025 – 16/11/2025 – 30/11/2025

4.2 Project Phase-Exit Review Checklist Develop a checklist to evaluate project readiness and confirm completion of deliverables before moving to the next phase. Estimate: 30 min (per iteration) Responsible: Maria Beili Mena Dorado (REP) Due date: 12/10/2025 – 26/10/2025 – 09/11/2025 – 23/11/2025 – 07/12/2025

5.1.1 Individual Participant Registration Sign up individually to the AB challenge. Estimate: 10 min Responsible: Maria Beili Mena Dorado (REP) Due date: 12/10/2025

5.1.2 Group Project Registration Send our team registration to the AB challenge. Estimate: 1 hour Responsible: Maria Beili Mena Dorado (REP) Due date: 19/10/2025

5.2 Final Project Submission CANCELLED → not chosen in the AB challenge Compile and submit the final version of project deliverables for evaluation and approval. Estimate: 15 min Responsible: Maria Beili Mena Dorado (REP) Due date: 21/12/2025

5.3 Final Project Presentation CANCELLED → not chosen in the AB challenge Prepare and deliver the final presentation summarizing key findings, results, and recommendations. This will only happen if we are one of the finalists. Estimate: 10 hours Responsible: Martí Vilaró (PM) Due date: 28/01/2026

6.1 AB Data Collection Sign the document and wait for AB to send the data. Estimate: 1 hour Responsible: Maria Beili Mena Dorado (REP) Due date: 02/11/2025

6.2.1 Assess External Data Need Determine whether additional external data sources are needed to supplement project analysis. Estimate: 1.5 hours Responsible: Martí Vilaró (PM) Due date: 02/11/2025

6.2.2 Collect External Data Acquire and validate external datasets in accordance with project data quality and compliance standards. Estimate: 4 hours Responsible: Alex Fernández de Alarcon (PCT) Due date: 02/11/2025

7.1 Implementation of Exploratory Data Analysis Conduct exploratory data analysis to identify trends, patterns, and anomalies in the collected data. Estimate: 3 hours Responsible: Sergi Rodríguez (PCT) Due date: 09/11/2025

7.2 Evaluation of Exploratory Data Analysis Review and interpret EDA results to refine data understanding and inform modeling decisions. Estimate: 1 hour Responsible: Pol Serrat (PCT) Due date: 09/11/2025

7.3 Refine Data Clean, transform, and format data to prepare it for advanced analysis and modeling based on the EDA. Estimate: 2 hours Responsible: Pol Serrat (PCT) Due date: 09/11/2025

8.1 Assess Models Usefulness Evaluate potential analytical models for their suitability, relevance, and alignment with project objectives. Estimate: 1.5 hours Responsible: Martí Vilaró (PM) Due date: 16/11/2025

8.2 Implement Models Develop and configure selected models, ensuring accurate integration with project data. Estimate: 6 hours Responsible: Sergi Rodríguez (PCT) Due date: 16/11/2025

8.3 Train Models Train models using prepared datasets to optimize accuracy and predictive performance. Estimate: 3 hours Responsible: Ferran Sordé (PCT) Due date: 16/11/2025

9.1 Implementation of Models Evaluation Test and evaluate model performance against validation data to assess accuracy and reliability. Estimate: 2 hours Responsible: Sergi Rodríguez (PCT) Due date: 16/11/2025

9.2 Improve Models Refine and adjust model parameters to enhance performance and correct identified deficiencies based on the models evaluation. Estimate: 5 hours Responsible: Ferran Sordé (PCT) Due date: 16/11/2025

10.1 Design of the Graphical Interface Structure Create the layout and structure for the project’s graphical user interface, focusing on usability and design logic. Estimate: 2 hours Responsible: Alex Fernández de Alarcon (PCT) Due date: 23/11/2025

10.2 Implementation of the Graphical Interface Code Develop and test the functional code for the graphical interface based on approved design specifications. Estimate: 2 hours Responsible: Sergi Rodríguez (PCT) Due date: 23/11/2025

- Communications Management

Every Sunday we will meet via Zoom to do a review about the current status of the project, how and when we do the remaining work, new changes to take into consideration, modifications, etc. We stay in touch via email and phone messages to communicate updates at any time.

- Configuration Management

To work in real time and together, we have created a shared directory on Google Drive, with all the needed documents. The data collection, exploratory data analysis, models selection and training, and models evaluation and improvement will be executed on the shared Google Drive session via collabs. The model integration will be managed through a GitHub repository.