UPF – Gestió de projectes

Challenge Final Report

Aigua Clara

Document Control Information

| Settings | Value |
| --- | --- |
| Document Title: | Challenge Final Report |
| Project Title: | Aigua Clara |
| Team Number: | 202.A |
| Project Owner: | Aigües de Barcelona (AB), Sheila Piñol |
| Project Core Team (PCT): | Maria Beili Mena Dorado (REP), Alex Fernández de Alarcon, Sergi Rodríguez, Pol Serrat, Ferran Sordé i Martí Vilaró (PM) |
| Project Representative | Maria Beili Mena Dorado |
| Project Manager | Martí Vilaró |

| Revision | Date | Created by | Short Description of Changes |
| --- | --- | --- | --- |
| v0.1 | 30/nov/25 | PCT | First draft of the Challenge Final Report |

The latest version of this controlled document is stored in Google Drive\GP2025-26\Subject global documents\Project methodology and templates\

Table of contents

1. Introduction	6

1.1. Executive summary	6

1.2. Success Criteria and Critical Success Factors	6

2. Background	7

3. Deliverables	7

4. Justification	8

2) Transparency for the client	8

3) Added value beyond the initial scope	8

5. Assumptions	8

6. Challenges	8

7. Next steps	9

# Introduction

## Executive summary

Advanced data analysis and machine learning techniques make it possible to detect abnormal water consumption patterns and anticipate issues such as leaks, technical failures, or unexpected behaviour. This project focuses on developing a first functional prototype capable of analysing real smart-meter data from Aigües de Barcelona to identify anomalous consumption patterns.

Throughout the project, we have cleaned, processed, enriched, and analysed the dataset, tested anomaly detection models, and developed a categorisation function that can be applied to new records. Although the project has faced several technical and resource constraints, we have built a solid foundation that Aigües de Barcelona can use as a starting point for a fully deployable anomaly detection system.

This final report summarises what we built, why we built it this way, the main challenges we faced, and the next steps needed to move the project forward.

## Success Criteria and Critical Success Factors

Success Criteria

The objective is to create a technological solution that allows for the automatic detection of anomalies in user consumption to prevent and find unusual patterns such as leaks. Success is measured based on whether the result obtained for our service coincides with a real case of anomalous consumption and whether this can be detected in advance. The SMART objectives are the following:

- Project objectives: meet all the milestones of the work plan within the established deadlines.

- Product objectives: achieve a minimum accuracy of 75% in the detection of anomalies in the analyzed data.

- Business objectives: demonstrate the technical feasibility and social value of the project to Aigües de Barcelona, ​​highlighting its positive impact on sustainability and efficiency.

Basically, transform the environment and consumption of people in the metropolitan area of ​​Barcelona by improving management and promoting responsible consumption.

Critical Success Factors

In order to successfully complete the project, we need the involvement of all stakeholders, good data quality, dedication from team members in the development of the project and having clear Statements and outs from the team and the mentor. It will also be necessary for team members to have the necessary technical knowledge to develop the alert system.

# 2. Background

As students at Universitat Pompeu Fabra, we share a strong environmental awareness and the willingness to contribute to projects that positively impact the Barcelona metropolitan area. Water is a limited and essential resource, and improving its management is key for sustainability.

This is why we chose the challenge proposed by Aigües de Barcelona: detecting abnormal consumption patterns through real-world data. It allows us to apply our knowledge in data analysis and machine learning to a meaningful problem that directly affects our community.

# 3. Deliverables

Develop a functional prototype capable of detecting patterns of anomalies in the water consumption of Aigües de Barcelona users using Machine Learning algorithms.

We've done:

- Data Processing

  - Complete cleaning and preprocessing of the dataset provided by AB.

  - Dataset enrichment using external information such as the municipal water price dataset.

  - Standardisation of the geographical variable using Idescat codes to merge heterogeneous datasets

- Analysis

  - Exploratory Data Analysis (EDA) of both raw and enriched datasets.

  - Analysis of correlations, distributions, consumption profiles, and anomaly patterns.

- Modelling

  - Development of a full preprocessing and engineering pipeline.

  - Testing simple but viable machine-learning models: Random Forest and Isolation Forest.

  - A functional anomaly categorisation function that can classify new unseen cases.

To deliver:

- Trained model for future use

- All the code used (data cleaning, merging, modelling).

- Functional categorisation pipeline ready for reuse and improvement.

# 4. Justification

Our decisions were based on three main criteria:

1) Feasibility within available resources

Given the time constraints, limited computing power, and the volume of data, we prioritised interpretable and computationally efficient models that we could deliver reliably.

### 2) Transparency for the client

AB needs a system that is easy to maintain, explain, and improve. Complex models (neural networks, LSTMs) were not necessary at this stage and would not have added realistic value under the current constraints.

### 3) Added value beyond the initial scope

We enriched the dataset with water-price information because it could be relevant for future socio-economic or tariff-related analyses and adds depth to the anomaly detection pipeline.

# 5. Assumptions

We assumed that the dataset provided by Aigües de Barcelona would be more structured and clean, so we could start developing the model earlier without dedicating so much time to fixing inconsistencies or missing data.

We also expected that our team would be selected in the first stage of the challenge, mainly because our proposal aligned well with the client’s needs. Even though this didn’t happen, it didn’t affect our motivation or the core idea of our project and we continued with the same focus from the beginning.

# 6. Challenges

One of the main things we couldn’t implement was the graphical interface. Technically, we didn’t have the tools required to make it work: Streamlit is not compatible with Google Colab, and we don’t have access to an NVIDIA GPU or a proper environment to run it smoothly. Because of this, we focused our effort on the model and the pipeline instead of the interface.

# 7. Next steps

A natural next step would be to try different models and compare them to the ones we have already tested, to see whether we can achieve better performance or detect anomalies more precisely.

Also, developing the graphical interface using other software or hardware would make the solution much more complete and usable for Aigües de Barcelona. If the technical environment allows it, this should be one of the priorities moving forward.